## Slide 1: Town Of Tillsonburg 2022 Business Plan
Building, Planning & By-law

## Slide 2: 2022 Business Objectives
Project | Community Strategic Plan | Lead Accountability | Project Cost | Anticipated Completion
Review and implement CloudPermit customer payment integration | Goal –Tillsonburg will strive for excellence and accountability in government, providing effective and efficient services, information and opportunities to shape municipal initiatives. Strategic Direction – N/A Priority Project - N/A | CBO | $0 | Q2
Complete Amanda/CloudPermit Integration (carry-over) | Goal – Through community and regional partnerships, Tillsonburg will attract and retain a diverse range of businesses, creating employment opportunities for residents and a balanced tax base. Strategic Direction – Continue to streamline and expedite the building approval process. Priority Project- Ongoing - Continued roll-out and resourcing for Cloud based permit application system | CBO/County IT | $0 (Oxford County Funded) | Q1
Inspector Training/Consistency & Policy Review Program | Goal – Tillsonburg will strive for excellence and accountability in government, providing effective and efficient services, information and opportunities to shape municipal initiatives. Strategic Direction - Position Tillsonburg as a leader in the municipal sector. Priority Project- N/A | CBO/DCBO | $2500 | Ongoing
2022 Building Code Amendments – Notify/educate designers, contractor and general public | Goal – Tillsonburg will strive for excellence and accountability in government, providing effective and efficient services, information and opportunities to shape municipal initiatives. Strategic Direction - Position Tillsonburg as a leader in the municipal sector. Priority Project- N/A | DCBO | $1000 | Ongoing

## Slide 3: 2022 Business Objectives
Project | Community Strategic Plan | Lead Accountability | Project Cost | Anticipated Completion
By-Law Reviews – Building By-Law (carry-over), Garbage/Dumping By-Law (carry-over), Pool Enclosure By-law | Goal – Tillsonburg will strive for excellence and accountability in government, providing effective and efficient services, information and opportunities to shape municipal initiatives. Strategic Direction - Position Tillsonburg as a leader in the municipal sector. Priority Project- N/A | CBO/Building-By-Law Compliance Supervisor | $2500 | Q4
Central Area Design Study – Façade Improvement Program | Goal – The Town of Tillsonburg will accommodate and support sustainable growth. Strategic Direction – Promote, preserve and enhance the downtown core as the retail centre and community hub for Tillsonburg. Priority Project- N/A | Development Tech./BIA | Funded from Economic Devm’t | Q4
Implement Planning Application Web Portal & Digital Service Delivery | Goal – Through community and regional partnerships, Tillsonburg will attract and retain a diverse range of businesses, creating employment opportunities for residents and a balanced tax base. Strategic Direction – Continue to streamline and expedite the building approval process. Priority Project – Ongoing- Continued roll-out and resourcing for Cloud based permit application system | CBO/County | $0 (Oxford County Funded) | Q4

## Slide 4: 2022 Business Objectives
Project | Community Strategic Plan | Lead Accountability | Project Cost | Anticipated Completion
Review of Planning Process & Procedures (carry over) | Goal – Through community and regional partnerships, Tillsonburg will attract and retain a diverse range of businesses, creating employment opportunities for residents and a balanced tax base. Strategic Direction – Continue to streamline and expedite the building approval process. Priority Project- N/A | Development Tech./County Planner | $0 | Q3
Review and Implement Planning Options related to MMAH More Homes, More Choice: Ontario’s Housing Supply Action Plan - secondary dwelling units, tiny homes, etc. (carry over) | Goal – Within the community, Tillsonburg will strive to offer residents the amenities, services and attractions they require to enjoy balanced lifestyles. Strategic Direction –Work with Oxford County and community partners to ensure an adequate supply of affordable, attainable housing options. Priority Project- Immediate - Affordable housing collaboration with Oxford County Goal – The Town of Tillsonburg will accommodate and support sustainable growth. Strategic Direction –Work with Oxford County and the development community to proactively plan for a variety of housing options that are affordable and attainable for current and prospective residents. Priority Project- Immediate - Attainable housing plan | CBO/County Planner | $0 | Q2

## Slide 5: 2022 Business Objectives
Project | Community Strategic Plan | Lead Accountability | Project Cost | Anticipated Completion
Building/By-Law Communications & Compliance Blitz | Goal – Within the community, Tillsonburg will strive to offer residents the amenities, services and attractions they require to enjoy balanced lifestyles. Strategic Direction – N/A Priority Project- Short Term - Property standards review and enforcement plan | Building-By-Law Compliance Supervisor | (New FTE split with Building & Protection) | Q4

## Slide 6: Risks
Complex development/construction projects along with ongoing
increased volumes require significant amount of staff time resulting in
longer turn around times which can discourage development
Increase in the number of inspectors can cause inconsistencies
Ontario Building Code Changes cause frustration for contractors, developers and owners which require additional staff time/resources to educate
Increase in inquiries/complaint volumes result in longer response times reducing customer service
Lack of a planning web portal/digital service causes delays and developer frustrations.

## Slide 7: Opportunities
Improvement of departmental communications to community and
development industry creates positive outcomes and transparency
Strategic organization of personnel and ongoing training
reduces liability, provides consistency and business continuity.
Implementation of a planning application web portal and digital review
process will provide multiple efficiencies for the development
community and streamline development approvals.
Ongoing review of Central Area Design Study will provide a framework
for future opportunity and development of the downtown BIA area
By-Law review provides updates and clarification that are relevant to
current public needs

## Slide 8: Future Departmental Directions: 3 year outlook
2023
Ontario Building Code Act – re-evaluate service review
Affordable housing collaboration with Oxford County
Central Area Design Study
By-Law & Policy Review

## Slide 9: Future Departmental Directions: 3 year outlook
2024
Review Building & Planning digital service delivery
Affordable housing collaboration with Oxford County
Central Area Design Study
By-Law Review

## Slide 10: Future Departmental Directions: 3 year outlook
2025
Central Area Design Study
By-Law Review